## Sprint List
Sprint Plan

Sprint	Start	Days	End	Size	Status	Release Date	Goal	Increment
1	8/3/2009	3	8/5/2009	5	Released			1
2	8/6/2009	2	8/7/2009	0	Unplanned			1
3	8/8/2009	5	8/12/2009	3	Unplanned			1
4	8/13/2009	2	8/14/2009	1	Unplanned			2
5	8/15/2009	5	8/19/2009	0	Unplanned			2
6	8/20/2009	2	8/21/2009	0	Unplanned			2
7	8/22/2009	5	8/26/2009	0	Unplanned
8	8/27/2009	2	8/28/2009	0	Unplanned
9	8/29/2009	5	9/2/2009	0	Unplanned
10	9/3/2009	2	9/4/2009	0	Unplanned
					Unplanned
					Unplanned
					Unplanned
					Unplanned
					Unplanned
			Unallocated stories	0

## Bikemap Backlog
Product Backlog

Story ID	Story name	Status	Size	Sprint	Priority	Comments
1	Deployment structure	Done	1	1
2	Look and feel (new interface)	Done	1	1
3	Create github repository	Done	1	1
4	Start writing backlog	Done	1	1
5	Create blog	Done	1	1
6	Change interface	Done		2		Search form list with results, maps
7	Version 0.1	Ongoing		2
8
9	Change 500m hard coded distance rule	Done	3	3		List X number of closest stations
10	Geocoder optimization when locating point					sometimes takes a point far away from the wanted area
11
12	Search form	Planned	1	4		Change possible search parameters
13
14