## Sprint List
Sprint Plan

Sprint	Start	Days	End	Size	Status	Release Date	Goal	Increment
1	8/3/2009	3	8/5/2009	5	Released			1
2	8/6/2009	2	8/7/2009	0	Unplanned			1
3	8/8/2009	5	8/12/2009	3	Unplanned			1
4	8/13/2009	2	8/14/2009	1	Unplanned			2
5	8/15/2009	5	8/19/2009	0	Unplanned			2
6	8/20/2009	2	8/21/2009	0	Unplanned			2
7	8/22/2009	5	8/26/2009	0	Unplanned
8	8/27/2009	2	8/28/2009	0	Unplanned
9	8/29/2009	5	9/2/2009	0	Unplanned
10	9/3/2009	2	9/4/2009	0	Unplanned
					Unplanned
					Unplanned
					Unplanned
					Unplanned
					Unplanned
			Unallocated stories	0

## Bikemap Backlog
Product Backlog

Story ID	Story name	Status	Size	Sprint	Priority	Comments
1	Deployment structure	Done	1	1
2	Look and feel (new interface)	Done	1	1
3	Create github repository	Done	1	1
4	Start writing backlog	Done	1	1
5	Create blog	Done	1	1
6	Change interface	Done		2		Search form list with results, maps
7	Version 0.1	Done		2
8
9	Change 500m hard coded distance rule	Done	3	3		List X number of closest stations
10	Geocoder optimization when locating point					sometimes takes a point far away from the wanted area
11
12	Search form	Planned	1	4		Change possible search parameters
13	Bottom divider showing author, etc	Done				Add bottom divider with author name, contact email and version number
14	Look into search results for “show all”	Ongoing				drawAllMarkers lists a sorted array with the stations after having used DrawClosestMarkers (may be a feature)
15	Sample servlet	Done				Look into how servlets work
16	Add link to blog and github	Planned				link to blog and github from http://martin.elwin.com/citybikes/
17	clear markers instead of redrawing map	Done				clear all overlay markers on the map for each draw*Markers instead of redrawing the map with mapDraw
18	keep house when showing all after address search	Planned				make sure that the addressMarker stays intact or is re-put on the map when invoking drawAllMarkers after searching
19	Log searches in database	Done				log all searches in a mysql database with timestamp, address and coordinates
20	Investigate initial marker load				1	Sometimes markers do not show up when loading the page
21	Fix timestamp sent to db	Done				insert in a probably faulty format when writing to the db
22	Refactor servlet code for future expansion	Planned				Try to separate initiation of database from RegisterAddress.java as it probably should not be reused when adding other functions to the servlet