## Release Plan
Increment Plan

Incr.	Start	Days	End	Size	Status	Release Date	Goal
1	13.6.2006	42	24.7.2006	0
2	25.7.2006	42	4.9.2006	0

Template note: Increment plan is intended to collect individual sprints into larger releases. In smaller projects, this is not needed.

Sprint Plan

Sprint	Start	Days	End	Size	Status	Release Date	Goal	Increment
1	6/13/2006	14	6/26/2006	0	Planned		Planning	1
2	6/27/2006	14	7/10/2006	0	Planned		Specification and prototype development	1
3	7/11/2006	14	7/24/2006	0	Planned		Specification and prototype development	1
4	7/25/2006	14	8/7/2006	0	Planned		Specification and prototype development	2
5	8/8/2006	14	8/21/2006	0	Planned		Specification and prototype development, documentation	2
6	8/22/2006	14	9/4/2006	0	Planned		Usability test, documentation, prototype corrections	2
					Unplanned
					Unplanned
					Unplanned
					Unplanned
					Unplanned
					Unplanned
					Unplanned
					Unplanned
					Unplanned
			Unallocated stories	0

## Product Backlog
Product Backlog

Story ID	Story name	Status	Size	Sprint	Priority	Comments
1	Lägga upp struktur för deployment	Ongoing		1
2	Look and feel (nytt interface)	Ongoing		1
3	Github	Ongoing		1
4	Backlog	Ongoing		1
5	Blog	Planned		1
6		Planned
7	Twitter chat	Planned		2

## PB Burndown
Product Backlog Burndown Chart
					Velocity and Remaining Work
Original planned size			137		Sprint count	5
Count trend from last			3	sprints	Trend sprint count	3
					Trend offset	0					Note:
Velocity (points per sprint)					Sprints in Trend	3					In this chart, the tops of the bars show the amount of actual
Original estimate			30					(or planned) implemented functionality at the beginning of each sprint.
Last 3 sprints			25.0					The bottoms of the bars show the changes in project scope
Realized total average			25.0		Trend count	7					(i.e. if the amount of story points
Average last 8			25.0					in the project increases, the bottoms move lower). The length
Avg. worst 3 in last 8			25.0					of the bars indicate the estimated size of the project at the
Trend			25.0					beginning of each sprint.
					These hidden cells are used to draw the graph on this page. DO NOT DELETE!					The red line indicates the current planned scope.
Predictions - Completion at the end of sprint…
Original estimate - Min			3
Original estimate - Avg			5
Original estimate - Max			8		Standard Dev.	2.83
Last 3 sprints			6
Realized average			6		LastPlanned	28
Average last 8			6		LastRealized	0
Avg. worst 3 in last 8			6					Development Velocity
Trend			6
Realized + St. Dev			6
Realized - St. Dev			6

					Trend					Average Speeds
Sprint	Remain.Work	Planned Work	Realized Work	Current Total Size	Col top	Do not delete…		Col bottom		Trend Help	Raw Trend	Real Trend	Current Bottom	Realized	Last 8	Worst 3 in Last 8
1	137	23	23	137	137	137	0	0		137	137.67	137.67	0	25.0	25.0	25.0
2	114	29	27	137	114	114	0	0		114	112.67	112.67	0	25.0	25.0	25.0
3	87	31		137	87	87	0	0		87	87.67	87.67	0	25.0	25.0	25.0
4	56	28		137	0	0	56	56		56	62.67	62.67	0	25.0	25.0	25.0
5	28	28		137	0	0	28	28		28	37.67	37.67	0	25.0	25.0	25.0
6					12.67	12.67	0	25.0	25.0	25.0
7					0	0	0	25.0	25.0	25.0
8					0		0	25.0	25.0	25.0
9					0		0	25.0	25.0	25.0
10					0		0	25.0	25.0	25.0
11					0		0	25.0	25.0	25.0
12					0		0	25.0	25.0	25.0
13					0		0	25.0	25.0	25.0
14					0		0	25.0	25.0	25.0
15					0		0	25.0	25.0	25.0
16					0		0	25.0	25.0	25.0
17					0		0	25.0	25.0	25.0
18					0		0	25.0	25.0	25.0
19					0		0	25.0	25.0	25.0
20					0		0	25.0	25.0	25.0
21					0		0	25.0	25.0	25.0
22					0		0	25.0	25.0	25.0
23					0		0	25.0	25.0	25.0
24					0		0	25.0	25.0	25.0

## Sp1
Sprint 1 Backlog		Work Remaining (h)

Sprint implementation days	5			Effort	Remaining on implementation day…
Trend calculated based on last	5	Days	Totals	33	33	30	23	21
Task rows	4	Done days	4		33	26.4	19.8	13.2	6.6
Warning! These are necessary		Trend			33.2	28.9	24.6	20.3	16	11.7	7.4	3.1
template rows		Trend Days	4		1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25
Task name	Story ID	Responsible	Status	Est.	1	2	3	4	5
Example task	1	Danny Dev	Done	5	5	2	0
Example task 2	1	Tina Tester	Ongoing	7	7	7	2	2
Example task 3	2	Danny Dev	Ongoing	12	12	12	12	10
<Delete these example lines>	2		Planned	9	9	9	9	9

## Sprint Sheet Template
Sprint 1 Backlog		Work Remaining (h)

Sprint implementation days	5			Effort	Remaining on implementation day…
Trend calculated based on last	5	Days	Totals	0	0
Task rows	1	Done days	1		0	0	0	0	0
Warning! These are necessary		Trend			-1.#NAN	-1.#NAN	-1.#NAN	-1.#NAN	-1.#NAN	-1.#NAN	-1.#NAN	-1.#NAN	-1.#NAN	-1.#NAN	-1.#NAN	-1.#NAN	-1.#NAN	-1.#NAN	-1.#NAN	-1.#NAN	-1.#NAN	-1.#NAN	-1.#NAN	-1.#NAN	-1.#NAN	-1.#NAN	-1.#NAN	-1.#NAN	-1.#NAN
template rows		Trend Days	1		1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25
Task name	Story ID	Responsible	Status	Est.	1	2	3	4	5

## Task Slips
Story ID:	1	Story:	This is a sample story
Task:	Example task

Responsible Person: Danny Dev
Initial / Estimate	5	Work / Done		Work / Left

Story ID:	1	Story:	This is a sample story
Task:	Example task 2

Responsible Person: Tina Tester
Initial / Estimate	7	Work / Done		Work / Left

Story ID:	2	Story:	This is another sample story
Task:	Example task 3

Responsible Person: Danny Dev
Initial / Estimate	12	Work / Done		Work / Left

Story ID:	2	Story:	This is another sample story
Task:	<Delete these example lines>

Responsible Person:
Initial / Estimate	9	Work / Done		Work / Left